## Sheet1
S.No | Task Detail | Assignment Date | Start Date | Deadline Date | Status | Responsible Person | Completed Date | Remark
Product
1 | Dashboard Home | 2021-02-08 | 2021-02-12 | 2021-02-28 | In Queue | Yash Gaur |  | Previous Design Revised
2 | Dashboard Login | 2021-02-13 | 2021-02-13 | 2021-02-28 | Partially Completed | Both |  | Design ready
3 | Distributor Profile | 2021-02-13 | 2021-02-15 | 2021-02-28 | Done | Yash Gaur |  | Ready With New Design
4 | Product Master
| Categories (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-02-17 | 2021-02-28 | Done | Both |  | Edit Section Remaining
| Sub Categories (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-02-18 | 2021-02-28 | Done | Both |  | Edit Section Remaining
| Product (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-02-24 | 2021-02-28 | Done | Both |  | Complete
| Pkt/Bag (Create, View, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-03-02 | 2021-02-28 | Done | Both |  | Complete
| Add Payout | 2021-02-17 |  | 2021-02-28 | In Queue | Both |  | Left in remaining due to need of further modules
| Waste/Damage Stock | 2021-02-17 |  | 2021-02-28 | In Queue | Both
Sales Executive
1 | Sales Executive Details & User Login Clear | 2021-03-11 | 2021-03-11 | 2021-03-15 | Done | Raghvendra | 2021-03-11
2 | Sales Executive Edit & Change Password | 2021-03-12 | 2021-03-12 | 2021-03-15 | Done | Raghvendra | 2021-03-12
3 | FSE Stock Return | 2021-03-13 | 2021-03-13 | 2021-03-15 | In Queue | Raghvendra
4 | User Status Change | 2021-03-13 |  | 2021-03-15 | In Queue
5 | Individual User Stock Detail | 2021-03-13 |  | 2021-03-15 | In Queue
Purchase
1 | Add Party | 2021-03-11 | 2021-03-11 | 2021-03-15 | Done | Yash | 2021-03-11
2 | Party List | 2021-03-12 | 2021-03-12 | 2021-03-15 | Partially Complete | Yash | 2021-03-12 | Party Purchase Bill Detail Remaining
3 | Add Stock | 2021-03-13 | 2021-03-13 | 2021-03-15 | In Queue | Yash | 2021-03-13
4 | Credit List | 2021-03-13 |  | 2021-03-22 | In Queue | Yash
5 | Generate Debit Note | 2021-03-13 |  | 2021-03-22 | In Queue | Yash
6 | Primary Order Replacement | 2021-03-13 |  | 2021-03-22 | In Queue | Yash